## City Plan (H2) (hidden)
[6 empty] | Kondisi Ideal |  |  |  | Estimasi Penyelesaian Project
No | Target City | Type | Priority | Collection | Target Navigable UKM | Target Productivity per Week | Dax Number | Dax Number (80 UKM/Week) | Dax Number (100 UKM/Week) | Week Estimation (80 UKM/Week) | Week Estimation (100 UKM/Week) | Month Estimation (80 UKM/Week) | Month Estimation (100 UKM/Week) | Driver Status | Status | Remarks | Collection Timeline |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  |  | Week Counts
[5 empty] | Satuan: UKM | Satuan: UKM/Week | Satuan: DAX | Satuan: DAX | Satuan: DAX | Satuan: Week | Satuan: Week | Satuan: Month | Satuan: Month |  |  |  | Target City | Week Estimation | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W1
1 | Samarinda |  | #N/A | [10 empty] | Samarinda | 1 Dax KC2 Samarinda
2 | Balikpapan | Expansion | P1 PGM, P1 Atlas |  | 995.81 | 39.8324 | 1 | 0.4979 | 0.39832 | 12.4476 | 9.9581 | 4 | 3 | mobility from Samarinda | 1 Dax KC2 Samarinda |  | Balikpapan | 12.4476 | bar: July W27 to October W41
3 | Nusantara (IKN) | Expansion | Adhoc |  | 467.88 | 18.7152 | 1 | 0.23394 | 0.18715 | 5.8485 | 4.6788 | 2 | 2 | mobility from Samarinda | 1 Dax KC2 Samarinda
4 | Banjar | Expansion | P1 PGM |  | 381.3 | 15.252 | 1 | 0.19065 | 0.15252 | 4.7662 | 3.813 | 2 | 1 | mobility from Bandung | 7 Dax KC2 Bandung |  | Banjar | 4.7662
5 | Pangandaran | Expansion | P1 PGM |  | 787.67 | 31.5068 | 1 | 0.39383 | 0.31507 | 9.8459 | 7.8767 | 3 | 2 | mobility from Bandung | 7 Dax KC2 Bandung |  | Pangandaran | 9.8459 | bar: October W44 to December W49
6 | Pelabuhan Ratu | #N/A | P1 PGM, P1 Atlas | Q3 | #N/A | #VALUE! | 1 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | mobility from Bandung | 7 Dax KC2 Bandung |  | Pelabuhan Ratu | #VALUE! | bar: August W32 to October W42
7 | Sukabumi | Maintenance | P2 Atlas |  | 8359.7 | 334.388 | 1 | 4.1799 | 3.3439 | 104.4963 | 83.597 | 27 | 21 | mobility from Bandung | 7 Dax KC2 Bandung
8 | Garut | Maintenance | P2 Atlas |  | 6682.27 | 267.2908 | 1 | 3.3411 | 2.6729 | 83.5284 | 66.8227 | 21 | 17 | mobility from Bandung | 7 Dax KC2 Bandung
9 | Cirebon |  | #N/A | [10 empty] | mobility from Bandung | 7 Dax KC2 Bandung
10 | Tasikmalaya |  | #N/A | [10 empty] | mobility from Bandung | 7 Dax KC2 Bandung
11 | Purwakarta |  | #N/A | [10 empty] | mobility from Bandung | 7 Dax KC2 Bandung
12 | Cianjur | #N/A | #N/A | [10 empty] | mobility from Bandung | 7 Dax KC2 Bandung
13 | Bangka | Expansion | P1 PGM | Q3 | 683.21 | 27.3284 | 1 | 0.34161 | 0.27328 | 8.5401 | 6.8321 | 3 | 2 | mobility from Pangkal Pinang | 1 Dax KC2 Pangkal Pinang |  | Bangka | 8.5401 | bar: August W32 to September W37
14 | Tanjung Pandan | Maintenance | P2 Atlas |  | 4646.75 | 185.87 | 1 | 2.3234 | 1.8587 | 58.0844 | 46.4675 | 15 | 12 | mobility from Pangkal Pinang | 1 Dax KC2 Pangkal Pinang
15 | Pangkal Pinang |  | #N/A | [10 empty] | Pangkal Pinang | 1 Dax KC2 Pangkal Pinang
16 | Barito Selatan | Expansion | P1 PGM | Q3 | 19.73 | 0.7892 | 1 | 0.009865 | 0.007892 | 0.24662 | 0.1973 | 1 | 1 | mobility from Palangkaraya | 1 Dax KC2 Palangkaraya |  | Barito Selatan | 0.24662 | bar: July W27 to September W36
17 | Barito Timur | Expansion | P1 PGM | Q3 | 151.79 | 6.0716 | 1 | 0.075895 | 0.060716 | 1.8974 | 1.5179 | 1 | 1 | mobility from Palangkaraya | 1 Dax KC2 Palangkaraya |  | Barito Timur | 1.8974 | bar: July W31
18 | Katingan | Expansion | P1 PGM | Q3 | 172.09 | 6.8836 | 1 | 0.086045 | 0.068836 | 2.1511 | 1.7209 | 1 | 1 | mobility from Palangkaraya | 1 Dax KC2 Palangkaraya |  | Katingan | 2.1511 | bar: August W33 to August W35
19 | Palangkaraya | Maintenance | P1 Atlas | Q3 | 1577.53 | 63.1012 | 1 | 0.78876 | 0.63101 | 19.7191 | 15.7753 | 5 | 4 | Palangkaraya | 1 Dax KC2 Palangkaraya
20 | Batu Bara | Expansion | P1 PGM | Q3 | 449.04 | 17.9616 | 1 | 0.22452 | 0.17962 | 5.613 | 4.4904 | 2 | 2 | mobility from Medan | 3 Dax KC2 Medan |  | Batu Bara | 5.613 | bar: July W27 to July W29
21 | Tanjung Balai | Expansion | P1 PGM | Q3 | 128.58 | 5.1432 | 1 | 0.06429 | 0.051432 | 1.6073 | 1.2858 | 1 | 1 | mobility from Medan | 3 Dax KC2 Medan |  | Tanjung Balai | 1.6073 | bar: August W35 to September W36
22 | Pematang Siantar | Expansion | Adhoc Mas Ujang | Q3 | 1318.93 | [8 empty] | Mobility from Medan | 3 Dax KC2 Medan
23 | Balige | Expansion | Adhoc Mas Ujang | Q3 | 305.88 | [8 empty] | Mobility from Medan | 3 Dax KC2 Medan
24 | Lebak | Expansion | P1 PGM, P1 Atlas |  | 571.31 | 22.8524 | 1 | 0.28565 | 0.22852 | 7.1414 | 5.7131 | 2 | 2 | mobility from Jabo | 2 Dax KC2 Jabo |  | Lebak | 7.1414 | bar: July W27 to August W35
25 | Pandeglang | Expansion | P1 PGM, P1 Atlas |  | 464.75 | 18.59 | 2 | 0.23237 | 0.1859 | 2.9047 | 2.3237 | 1 | 1 | mobility from Jabo | 2 Dax KC2 Jabo |  | Pandeglang | 2.9047 | bar: September W37 to October W43
26 | Karawang | Maintenance | P2 Atlas |  | 8293.49 | 331.7396 | 1 | 4.1467 | 3.3174 | 103.6686 | 82.9349 | 26 | 21 | Mobility from Jabo | 1 Dax KC2 Jabo
27 | Serang |  | #N/A |  |  | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | mobility from Jabo | 2 Dax KC2 Jabo
28 | Cilegon | Expansion | Adhoc Mas Ujang | Q3 | 1054.88 | 42.1952 | 1 | 0.52744 | 0.42195 | 13.186 | 10.5488 | 4 | 3 | mobility from Jabo | 2 Dax KC2 Jabo
29 | Aceh |  | #N/A |  |  | #VALUE! |  | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | Banda Aceh | 1 Dax KC2 Aceh
30 | Kota Langsa | Expansion | P1 PGM |  | 445.81 | 17.8324 | 1 | 0.2229 | 0.17832 | 5.5726 | 4.4581 | 2 | 2 | mobility from Aceh | 1 Dax KC2 Aceh |  | Kota Langsa | 5.5726 | bar: October W40 to November W46
31 | Bener Meriah | Expansion | P1 PGM | Q3 | 362.88 | 14.5152 | 1 | 0.18144 | 0.14515 | 4.536 | 3.6288 | 2 | 1 | mobility from Aceh | 1 Dax KC2 Aceh |  | Bener Meriah | 4.536 | bar: July W31 to September W36
32 | Kota Sabang | Expansion | P1 PGM | Q3 | 146.91 | 5.8764 | 1 | 0.073455 | 0.058764 | 1.8364 | 1.4691 | 1 | 1 | mobility from Aceh | 1 Dax KC2 Aceh |  | Kota Sabang | 1.8364 | bar: July W27 to July W28
33 | Lhokseumawe | Expansion | P1 PGM |  | 503.57 | 20.1428 | 1 | 0.25179 | 0.20143 | 6.2946 | 5.0357 | 2 | 2 | mobility from Aceh | 1 Dax KC2 Aceh |  | Lhokseumawe | 6.2946 | bar: September W38 to November W45
34 | Bintan | Expansion | P1 PGM |  | 279.64 | 11.1856 | 1 | 0.13982 | 0.11186 | 3.4955 | 2.7964 | 1 | 1 | mobility from Batam | 1 Dax KC2 Batam |  | Bintan | 3.4955 | bar: July W27 to July W30
35 | Batam |  | #N/A | [10 empty] | Batam | 1 Dax KC2 Batam
36 | Padang | Maintenance | P1 Atlas | Q4 | 2770.25 | 110.81 | 1 | 1.3851 | 1.1081 | 34.6281 | 27.7025 | 9 | 7 | Padang | 1 Dax KC360 Padang |  | Padang | 34.6281 | bar: July W27 to September W37
37 | Dharmasraya | Expansion | P1 PGM | Q4 | 377.59 | 15.1036 | 1 | 0.18879 | 0.15104 | 4.7199 | 3.7759 | 2 | 1 | mobility from Padang | 1 Dax KC360 Padang |  | Dharmasraya | 4.7199 | bar: July W27 to August W32
38 | Kota Sawahlunto | Expansion | P1 PGM | Q4 | 183.05 | 7.322 | 1 | 0.091525 | 0.07322 | 2.2881 | 1.8305 | 1 | 1 | mobility from Padang | 1 Dax KC360 Padang |  | Kota Sawahlunto | 2.2881 | bar: August W34 to September W36
39 | Kota Solok | Expansion | P1 PGM | Q4 | 258.4 | 10.336 | 1 | 0.1292 | 0.10336 | 3.23 | 2.584 | 1 | 1 | mobility from Padang | 1 Dax KC360 Padang |  | Kota Solok | 3.23 | bar: September W38 to October W41
40 | Pasaman Barat | Expansion | P1 PGM | Q4 | 447.31 | 17.8924 | 1 | 0.22365 | 0.17892 | 5.5914 | 4.4731 | 2 | 2 | mobility from Padang | 1 Dax KC360 Padang |  | Pasaman Barat | 5.5914 | bar: October W43 to December W49
41 | Kendari | #N/A | #N/A | [10 empty] | Kendari | 1 Dax KC2 Kendari
42 | Enrekang | Expansion | P1 PGM | Q3 | 119.1 | 4.764 | 1 | 0.05955 | 0.04764 | 1.4888 | 1.191 | 1 | 1 | mobility from Kendari | 1 Dax KC2 Kendari |  | Enrekang | 1.4888 | bar: July W27 to July W28
43 | Luwu Utara | Expansion | P1 PGM | Q3 | 471.73 | 18.8692 | 1 | 0.23586 | 0.18869 | 5.8966 | 4.7173 | 2 | 2 | mobility from Kendari | 1 Dax KC2 Kendari |  | Luwu Utara | 5.8966 | bar: July W27 to August W33
44 | Banjarmasin |  | #N/A | [10 empty] | Banjarmasin | 1 Dax KC2 Banjarmasin
45 | Hulu Sungai Utara | Expansion | P1 PGM, P1 Atlas | Q3 | 541.44 | 21.6576 | 1 | 0.27072 | 0.21658 | 6.768 | 5.4144 | 2 | 2 | mobility from Banjarmasin | 1 Dax KC2 Banjarmasin |  | Hulu Sungai Utara | 6.768
46 | Kotabaru | Expansion | P1 PGM | Q3 | 1463.92 | 58.5568 | 1 | 0.73196 | 0.58557 | 18.299 | 14.6392 | 5 | 4 | mobility from Banjarmasin | 1 Dax KC2 Banjarmasin |  | Kotabaru | 18.299 | bar: July W27 to September W37
47 | Tabalong | Expansion | P1 PGM, P1 Atlas | Q3 | 599.9 | 23.996 | 1 | 0.29995 | 0.23996 | 7.4987 | 5.999 | 2 | 2 | mobility from Banjarmasin | 1 Dax KC2 Banjarmasin |  | Tabalong | 7.4987 | bar: July W27 to August W35
48 | Pekanbaru |  | #N/A | [10 empty] | Pekanbaru | 1 Dax KC2 Pekanbaru
49 | Indragiri Hilir | Expansion | P1 PGM | Q3 | 340.44 | 13.6176 | 1 | 0.17022 | 0.13618 | 4.2555 | 3.4044 | 2 | 1 | mobility from Pekanbaru | 1 Dax KC2 Pekanbaru |  | Indragiri Hilir | 4.2555 | bar: July W27 to July W31
50 | Sibolga | Expansion | P2 Atlas |  | 111.48 | 4.4592 | 1 | 0.05574 | 0.044592 | 1.3935 | 1.1148 | 1 | 1 | mobility from Pekanbaru | 1 Dax KC2 Pekanbaru
51 | Dumai |  | #N/A | [10 empty] | mobility from Pekanbaru | 1 Dax KC2 Pekanbaru
52 | Labuan Bajo | Maintenance | P0 PGM |  | 182.28 | 7.2912 | 1 | 0.09114 | 0.072912 | 2.2785 | 1.8228 | 1 | 1 | no dax available | no dax available |  | Labuan Bajo | 2.2785
53 | Manggarai | Expansion | P1 PGM | Q4 | 196.45 | 7.858 | 1 | 0.098225 | 0.07858 | 2.4556 | 1.9645 | 1 | 1 | mobility from Labuan Bajo | no dax available |  | Manggarai | 2.4556 | bar: July W27 to July W29
54 | Pontianak | Maintenance | P1 Atlas | Q4 | 1887.01 | 75.4804 | 1 | 0.9435 | 0.7548 | 23.5876 | 18.8701 | 6 | 5 | Pontianak | 1 Dax KC360 Pontianak |  | Pontianak | 23.5876 | bar: September W38 to October W43
55 | Lamandau | Expansion | P1 PGM | Q4 | 526.03 | 21.0412 | 1 | 0.26301 | 0.21041 | 6.5754 | 5.2603 | 2 | 2 | mobility from Pontianak | 1 Dax KC360 Pontianak |  | Lamandau | 6.5754 | bar: April W15 to May W19
56 | Ketapang | Expansion | P1 Atlas | Q4 | 1023.59 | 40.9436 | 2 | 0.51179 | 0.40944 | 6.3974 | 5.1179 | 2 | 2 | mobility from Pontianak | 1 Dax KC360 Pontianak
57 | Lampung Utara | Expansion | P1 PGM |  | 1041.51 | 41.6604 | 1 | 0.52076 | 0.4166 | 13.0189 | 10.4151 | 4 | 3 | mobility from Lampung | 3 Dax KC2 Lampung |  | Lampung Utara | 13.0189 | bar: July W29 to August W33
58 | Lampung |  | #N/A | [10 empty] | Lampung | 3 Dax KC2 Lampung
59 | Tanggamus | Expansion | P1 PGM | Q3 | 68.19 | 2.7276 | 1 | 0.034095 | 0.027276 | 0.85237 | 0.6819 | 1 | 1 | mobility from Lampung | 3 Dax KC2 Lampung |  | Tanggamus | 0.85237 | bar: July W27
60 | Tulang Bawang | Expansion | P1 PGM | Q3 | 386.66 | 15.4664 | 1 | 0.19333 | 0.15466 | 4.8332 | 3.8666 | 2 | 1 | mobility from Lampung | 3 Dax KC2 Lampung |  | Tulang Bawang | 4.8332 | bar: September W37 to October W42
61 | Tulang Bawang Barat | Expansion | P1 PGM | Q3 | 614 | 24.56 | 1 | 0.307 | 0.2456 | 7.675 | 6.14 | 2 | 2 | mobility from Lampung | 3 Dax KC2 Lampung |  | Tulang Bawang Barat | 7.675 | bar: July W27 to August W35
62 | Lebong | Expansion | P1 PGM |  | 38.09 | 1.5236 | 1 | 0.019045 | 0.015236 | 0.47612 | 0.3809 | 1 | 1 | mobility from Lubuk Linggau | 1 Dax KC2 Lubuk Linggau |  | Lebong | 0.47612 | bar: July W27
63 | Bengkulu | Maintenance | P1 Atlas | Q3 | 1600.95 | 64.038 | 1 | 0.80047 | 0.64038 | 20.0119 | 16.0095 | 6 | 5 | mobility from Lubuk Linggau | 1 Dax KC2 Lubuk Linggau |  | Bengkulu | 20.0119 | bar: July W27 to July W31
64 | Curup | Maintenance | P1 Atlas | Q3 | 939.18 | 37.5672 | 1 | 0.46959 | 0.37567 | 11.7397 | 9.3918 | 3 | 3 | mobility from Lubuk Linggau | 1 Dax KC2 Lubuk Linggau
65 | Lingga | Expansion | P1 PGM |  | 63.31 | 2.5324 | 1 | 0.031655 | 0.025324 | 0.79137 | 0.6331 | 1 | 1 | mobility from Prabumulih | 1 Dax KC2 Prabumulih |  | Lingga | 0.79137 | bar: July W27 to August W33
66 | Lahat | Maintenance | P1 Atlas | Q3 | 729.1 | 29.164 | 1 | 0.36455 | 0.29164 | 9.1137 | 7.291 | 3 | 2 | mobility from Prabumulih | 1 Dax KC2 Prabumulih
67 | Baturaja | #N/A | #N/A | [10 empty] | mobility from Prabumulih | 1 Dax KC2 Prabumulih
68 | Palu | Maintenance | P1 Atlas | Q3 | 1840.53 | 73.6212 | 1 | 0.92026 | 0.73621 | 23.0066 | 18.4053 | 6 | 5 | Palu | 1 Dax KC2 Palu
69 | Parigi Moutong | Expansion | P1 PGM | Q3 | 575.66 | 23.0264 | 1 | 0.28783 | 0.23026 | 7.1957 | 5.7566 | 2 | 2 | mobility from Palu | 1 Dax KC2 Palu |  | Parigi Moutong | 7.1957 | bar: July W27 to October W43
70 | Minahasa Selatan | Expansion | P1 PGM | Q3 | 798.77 | 31.9508 | 1 | 0.39938 | 0.31951 | 9.9846 | 7.9877 | 3 | 2 | mobility from Manado | 2 Dax KC2 Manado |  | Minahasa Selatan | 9.9846 | bar: July W27 to October W41
71 | Minahasa Tenggara | Expansion | P1 PGM | Q3 | 390.76 | 15.6304 | 1 | 0.19538 | 0.1563 | 4.8845 | 3.9076 | 2 | 1 | mobility from Manado | 2 Dax KC2 Manado |  | Minahasa Tenggara | 4.8845 | bar: July W31 to September W39
72 | Surabaya | Maintenance | P1 Atlas |  | 5957.62 | 238.3048 | 1 | 2.9788 | 2.383 | 74.4702 | 59.5762 | 19 | 15 | Surabaya | 5 Dax KC2 Surabaya |  | Surabaya | 74.4702 | bar: July W27 to August W32
73 | Jember |  | #N/A | [10 empty] | mobility from Surabaya | 5 Dax KC2 Surabaya
74 | Pekalongan |  | #N/A | [10 empty] | mobility from Semarang | 5 Dax KC2 Semarang
75 | Kudus |  | #N/A | [10 empty] | mobility from Semarang | 5 Dax KC2 Semarang
76 | Banyumas |  | #N/A | [10 empty] | mobility from Semarang | 5 Dax KC2 Semarang
77 | Madiun |  | #N/A | [10 empty] | mobility from Malang | 4 Dax KC2 Malang
78 | Kediri |  | #N/A | [10 empty] | mobility from Malang | 4 Dax KC2 Malang
79 | Kedu Raya |  | #N/A | [10 empty] | mobility from Yogyakarta | 5 Dax KC2 Yogyakarta
80 | Ternate | Maintenance | P0 Atlas |  | 308.69 | 12.3476 | 1 | 0.15434 | 0.12348 | 3.8586 | 3.0869 | 1 | 1 | Ternate |  |  | Ternate | 3.8586 | bar: July W27 to July W30
81 | Sumbawa Besar | Maintenance | P1 Atlas | Q3 | 374.29 | 14.9716 | 1 | 0.18714 | 0.14972 | 4.6786 | 3.7429 | 2 | 1 | mobility from Bima | 1 Dax KC2 Bima
82 | Sumba Timur | Expansion | P0 PGM, P1 Atlas |  | 323.82 | 12.9528 | 2 | 0.16191 | 0.12953 | 2.0239 | 1.6191 | 1 | 1 | Vendor |  |  | Sumba Timur | 2.0239 | bar: July W31 to October W41
83 | Tarakan | Maintenance | P1 Atlas |  | 768.57 | 30.7428 | 1 | 0.38429 | 0.30743 | 9.6071 | 7.6857 | 3 | 2 | Tarakan | 1 Dax KC360 Tarakan
84 | Mamuju | Maintenance | P2 Atlas |  | 1973.36 | 78.9344 | 1 | 0.98668 | 0.78934 | 24.667 | 19.7336 | 7 | 5 | Mamuju | 1 Dax KC360 Mamuju
85 | Ambon | Maintenance | P2 Atlas |  | 1113.24 | 44.5296 | 1 | 0.55662 | 0.4453 | 13.9155 | 11.1324 | 4 | 3 | Ambon | 1 Dax KC360 Ambon
86 | Kotamobagu | Maintenance | P2 Atlas |  | 487.27 | 19.4908 | 1 | 0.24363 | 0.19491 | 6.0909 | 4.8727 | 2 | 2 | Kotamobagu | 1 Dax KC360 Kotamobagu
87 | Makassar |  | #N/A | [10 empty] | Makassar | 2 Dax KC2 Makassar
88 | Jayapura |  | #N/A | [10 empty] | Jayapura | 1 Dax KC2 Jayapura
89 | Jambi |  | #N/A | [10 empty] | Jambi | 1 Dax Jambi
90 | Sintang | Expansion | P1 Atlas | Q4 | 39.28 | 1.5712 | 1 | 0.01964 | 0.015712 | 0.491 | 0.3928 | 1 | 1 | no dax available
91 | Manokwari | Expansion | P1 Atlas | Q4 | 399.93 | 15.9972 | 1 | 0.19997 | 0.15997 | 4.9991 | 3.9993 | 2 | 1 | no dax available
92 | Sumba Barat | Expansion | P0 PGM, P1 Atlas |  | 197.3 | 7.892 | 2 | 0.09865 | 0.07892 | 1.2331 | 0.9865 | 1 | 1 | Vendor
93 | Sikka |  |  |  | 210 | 8.4 | 1 | 0.105 | 0.084 | 2.625 | 2.1 | 1 | 1

## City Plan (P1) (hidden)
[5 empty] | Kondisi Ideal |  |  |  | Estimasi Penyelesaian Project
No | Target City | Type | Priority | Target Navigable UKM | Target Productivity per Week | Dax Number | Dax Number (80 UKM/Week) | Dax Number (100 UKM/Week) | Week Estimation (80 UKM/Week) | Week Estimation (100 UKM/Week) | Month Estimation (80 UKM/Week) | Month Estimation (100 UKM/Week) | Driver Status | Driver Availability | Status | Status 2H | Device | Remarks | Collection Timeline |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  |  | Week Counts
|  |  |  | Satuan: UKM | Satuan: UKM/Week | Satuan: DAX | Satuan: DAX | Satuan: DAX | Satuan: Week | Satuan: Week | Satuan: Month | Satuan: Month | [6 empty] | Target City | Week Estimation | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W1
1 | Balikpapan | Expansion | P1 PGM, P1 Atlas | 995.81 | 24.8952 | 1 | 0.31119 | 0.24895 | 12.4476 | 9.9581 | 4 | 3 | mobility from Samarinda | available 1 Dax KC2, 7 Dax KC360 | can start collection | Suggest to Start | Already Have |  | Balikpapan | 12.4476 | bar: July W27 to October W41
2 | Nusantara (IKN) | Expansion | Adhoc | 467.88 | 11.697 | 1 | 0.14621 | 0.11697 | 5.8485 | 4.6788 | 2 | 2 | mobility from Samarinda | available 1 Dax KC2, 7 Dax KC360 |  |  | Already Have |  | Nusantara (IKN) | 5.8485
3 | Banjar | Expansion | P1 PGM | 381.3 | 9.5325 | 3 | 0.11916 | 0.095325 | 1.5887 | 1.271 | 1 | 1 | mobility from Bandung | available 12 Dax (7 Dax KC2, 5 Dax KC360) 5 hours from Bandung | can start collection | Suggest to Start | Already Have |  | Banjar | 1.5887 | bar: October W44 to December W49
4 | Pangandaran | Expansion | P1 PGM | 787.67 | 19.6917 | 4 | 0.24615 | 0.19692 | 2.4615 | 1.9692 | 1 | 1 | mobility from Bandung | available 12 Dax (7 Dax KC2, 5 Dax KC360) 5 hour motorbike from Bandung | can start collection | Suggest to Start | Already Have |  | Pangandaran | 2.4615 | bar: August W32 to October W42
5 | Pelabuhan Ratu | #N/A | P1 PGM, P1 Atlas | #N/A | #VALUE! | 1 | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | mobility from Bandung | available 12 Dax (7 Dax KC2, 5 Dax KC360) 5 hour motorbike from Bandung | can start collection |  | Already Have |  | Pelabuhan Ratu | #VALUE! | bar: August W32 to September W37
6 | Bangka | Expansion | P1 PGM | 683.21 | 17.0802 | 1 | 0.2135 | 0.1708 | 8.5401 | 6.8321 | 3 | 2 | mobility from Pangkal Pinang | available 1 Dax KC2 1 hour from Pangkal Pinang | can start collection |  | Already Have |  | Bangka | 8.5401 | bar: July W27 to September W36
7 | Barito Selatan | Expansion | P1 PGM | 19.73 | 0.49325 | 1 | 0.0061656 | 0.0049325 | 0.24662 | 0.1973 | 1 | 1 | mobility from Palangkaraya | available 1 Dax KC360 5 hours from Palangkaraya |  |  | Already Have |  | Barito Selatan | 0.24662 | bar: July W31
8 | Barito Timur | Expansion | P1 PGM | 151.79 | 3.7947 | 1 | 0.047434 | 0.037947 | 1.8974 | 1.5179 | 1 | 1 | mobility from Palangkaraya | available 1 Dax KC360 5 hours from Palangkaraya |  |  | Already Have |  | Barito Timur | 1.8974 | bar: August W33 to August W35
9 | Katingan | Expansion | P1 PGM | 172.09 | 4.3022 | 1 | 0.053778 | 0.043022 | 2.1511 | 1.7209 | 1 | 1 | mobility from Palangkaraya | available 1 Dax KC360 5 hours from Palangkaraya |  | Suggest to Start | Already Have |  | Katingan | 2.1511 | bar: July W27 to July W29
10 | Palangkaraya | Maintenance | P1 Atlas | 1577.53 | 39.4382 | 1 | 0.49298 | 0.39438 | 19.7191 | 15.7753 | 5 | 4 | Palangkaraya | available 1 Dax KC2 |  | Suggest to Start | Already Have |  | Palangkaraya | 19.7191
11 | Batu Bara | Expansion | P1 PGM | 449.04 | 11.226 | 1 | 0.14033 | 0.11226 | 5.613 | 4.4904 | 2 | 2 | mobility from Medan | available 3 Dax KC2 4 hours from Medan |  | Suggest to Start | Already Have |  | Batu Bara | 5.613 | bar: August W32 to September W38
12 | Kota Langsa | Expansion | P1 PGM | 445.81 | 11.1452 | 1 | 0.13932 | 0.11145 | 5.5726 | 4.4581 | 2 | 2 | mobility from Medan | available 3 Dax KC2 4 hours from Medan |  |  | Already Have |  | Kota Langsa | 5.5726 | bar: October W40 to November W46
13 | Tanjung Balai | Expansion | P1 PGM | 128.58 | 3.2145 | 1 | 0.040181 | 0.032145 | 1.6073 | 1.2858 | 1 | 1 | mobility from Balige | available 7 Dax BYOD, 4 hours motorbike from Balige available 3 Dax KC2, 4 hours motorbike from Medan |  | Suggest to Start | Already Have |  | Tanjung Balai | 1.6073 | bar: August W35 to September W36
14 | Lebak | Expansion | P1 PGM, P1 Atlas | 571.31 | 14.2827 | 1 | 0.17853 | 0.14283 | 7.1414 | 5.7131 | 2 | 2 | Jabo | Available 2 Dax that domiciled in Tangerang (Dax KC2) 3 hours motorbike from Tangerang | can start collection |  | Already Have |  | Lebak | 7.1414 | bar: July W27 to August W35
15 | Pandeglang | Expansion | P1 PGM, P1 Atlas | 464.75 | 11.6188 | 2 | 0.14523 | 0.11619 | 2.9047 | 2.3237 | 1 | 1 | Jabo | Available 2 Dax that domiciled in Tangerang (Dax KC2) 3 hours motorbike from Tangerang | can start collection |  | Already Have |  | Pandeglang | 2.9047 | bar: September W37 to October W43
16 | Bener Meriah | Expansion | P1 PGM | 362.88 | 9.072 | 1 | 0.1134 | 0.09072 | 4.536 | 3.6288 | 2 | 1 | mobility from Aceh | available 1 Dax KC2 7 hours from Banda Aceh | can start collection |  | Already Have |  | Bener Meriah | 4.536 | bar: July W31 to September W36
17 | Kota Sabang | Expansion | P1 PGM | 146.91 | 3.6727 | 1 | 0.045909 | 0.036727 | 1.8364 | 1.4691 | 1 | 1 | mobility from Aceh | Available 16 Dax (1 Dax KC2, 15 Dax BYOD) 45 minutes by ship from Banda Aceh | can start collection | Suggest to Start | Already Have |  | Kota Sabang | 1.8364 | bar: July W27 to July W28
18 | Lhokseumawe | Expansion | P1 PGM | 503.57 | 12.5892 | 1 | 0.15737 | 0.12589 | 6.2946 | 5.0357 | 2 | 2 | mobility from Aceh | Available 16 Dax (1 Dax KC2, 15 Dax BYOD) 5,5 hours motorbike from Banda Aceh | can start collection |  | Already Have |  | Lhokseumawe | 6.2946 | bar: September W38 to November W45
19 | Bintan | Expansion | P1 PGM | 279.64 | 6.991 | 1 | 0.087387 | 0.06991 | 3.4955 | 2.7964 | 1 | 1 | mobility from Batam | available 2 Dax (1 Dax KC2, 1 Dax KC360) 3 hours from Batam | can start collection |  | Already Have | gridnya masuk tanjung pinang | Bintan | 3.4955 | bar: July W27 to July W30
20 | Dharmasraya | Expansion | P1 PGM | 377.59 | 9.4397 | 1 | 0.118 | 0.094397 | 4.7199 | 3.7759 | 2 | 1 | mobility from Padang | available 1 Dax KC360 5 hours from Padang |  |  | Need KC2 | have to contact Dax, then can start collection | Dharmasraya | 4.7199 | bar: July W27 to August W32
21 | Kota Sawahlunto | Expansion | P1 PGM | 183.05 | 4.5762 | 1 | 0.057203 | 0.045762 | 2.2881 | 1.8305 | 1 | 1 | mobility from Padang | Available 1 Dax (Dax KC360) 2,5 hours motorbike from Padang |  |  | Need KC2 | have to contact Dax, then can start collection | Kota Sawahlunto | 2.2881 | bar: August W34 to September W36
22 | Kota Solok | Expansion | P1 PGM | 258.4 | 6.46 | 1 | 0.08075 | 0.0646 | 3.23 | 2.584 | 1 | 1 | mobility from Padang | Available 1 Dax (Dax KC360) 1,5 hours motorbike from Padang |  |  | Need KC2 | have to contact Dax, then can start collection | Kota Solok | 3.23 | bar: September W38 to October W41
23 | Pasaman Barat | Expansion | P1 PGM | 447.31 | 11.1828 | 1 | 0.13978 | 0.11183 | 5.5914 | 4.4731 | 2 | 2 | mobility from Padang | available 1 Dax KC360 4 hours motorbike from Padang |  |  | Need KC2 | have to contact Dax, then can start collection | Pasaman Barat | 5.5914 | bar: October W43 to December W49
24 | Padang | Maintenance | P1 Atlas | 2770.25 | 69.2562 | 2 | 0.8657 | 0.69256 | 17.3141 | 13.8512 | 5 | 4 | Padang | available 1 Dax KC360 |  |  | Need KC2 |  | Padang | 17.3141
25 | Enrekang | Expansion | P1 PGM | 119.1 | 2.9775 | 1 | 0.037219 | 0.029775 | 1.4888 | 1.191 | 1 | 1 | mobility from Makassar plan B (mobility from Kendari) possible booster | available 3 Dax KC2 7 hours from Makassar | risk, too far away | Suggest to Start | Already Have |  | Enrekang | 1.4888 | bar: July W27 to July W28
26 | Hulu Sungai Utara | Expansion | P1 PGM, P1 Atlas | 541.44 | 13.536 | 1 | 0.1692 | 0.13536 | 6.768 | 5.4144 | 2 | 2 | mobility from Banjarmasin | available 2 Dax from Banjarmasin (1 Dax KC2, 1 Dax Kartacam 360) 4 hours motorbike from Banjarmasin |  |  | Already Have |  | Hulu Sungai Utara | 6.768
27 | Kotabaru | Expansion | P1 PGM | 1463.92 | 36.598 | 1 | 0.45747 | 0.36598 | 18.299 | 14.6392 | 5 | 4 | mobility from Banjarmasin | Available 4 Dax (1 Dax KC2, 3 Dax KC360) 6 hours motorbike from Banjarmasin | risk, too far away |  | Already Have |  | Kotabaru | 18.299 | bar: July W27 to September W37
28 | Tabalong | Expansion | P1 PGM, P1 Atlas | 599.9 | 14.9975 | 1 | 0.18747 | 0.14997 | 7.4987 | 5.999 | 2 | 2 | mobility from Banjarmasin | available 2 Dax from Banjarmasin (1 Dax KC2, 1 Dax Kartacam 360) 6 hours motorbike from Banjarmasin | risk, too far away |  | Already Have |  | Tabalong | 7.4987 | bar: July W27 to August W35
29 | Indragiri Hilir | Expansion | P1 PGM | 340.44 | 8.511 | 1 | 0.10639 | 0.08511 | 4.2555 | 3.4044 | 2 | 1 | mobility from Pekanbaru | available 3 Dax (1 Dax KC2, 2 Dax KC360) 6 hours from Pekanbaru | risk, too far away |  | Already Have |  | Indragiri Hilir | 4.2555 | bar: July W27 to July W31
30 | Manggarai | Expansion | P1 PGM | 196.45 | 4.9112 | 1 | 0.061391 | 0.049112 | 2.4556 | 1.9645 | 1 | 1 | mobility from Labuan Bajo | Available 2 Dax (Dax KC2) 4 hours motorbike from Labuan Bajo | risk, too far away |  | Already Have |  | Manggarai | 2.4556 | bar: July W27 to July W29
31 | Lampung Utara | Expansion | P1 PGM | 1041.51 | 26.0377 | 1 | 0.32547 | 0.26038 | 13.0189 | 10.4151 | 4 | 3 | mobility from Lampung | Available 3 Dax (1, Dax KC2, 2 Dax KC360) 3 hours motorbike from Bandar Lampung |  | Suggest to Start | Already Have |  | Lampung Utara | 13.0189 | bar: July W29 to August W33
32 | Tanggamus | Expansion | P1 PGM | 68.19 | 1.7047 | 1 | 0.021309 | 0.017048 | 0.85237 | 0.6819 | 1 | 1 | mobility from Lampung | available 3 Dax from Lampung (1 Dax KC2, 2 Dax Kartacam 360) 2,5 hours motorbike from Lampung |  | Suggest to Start | Already Have |  | Tanggamus | 0.85237 | bar: July W27
33 | Tulang Bawang | Expansion | P1 PGM | 386.66 | 9.6665 | 1 | 0.12083 | 0.096665 | 4.8332 | 3.8666 | 2 | 1 | mobility from Lampung | available 3 Dax from Lampung (1 Dax KC2, 2 Dax Kartacam 360) 4 hours motorbike from Lampung |  | Suggest to Start | Already Have |  | Tulang Bawang | 4.8332 | bar: September W37 to October W42
34 | Tulang Bawang Barat | Expansion | P1 PGM | 614 | 15.35 | 1 | 0.19187 | 0.1535 | 7.675 | 6.14 | 2 | 2 | mobility from Lampung | available 3 Dax from Lampung (1 Dax KC2, 2 Dax Kartacam 360) 3 hours motorbike from Lampung |  | Suggest to Start | Already Have |  | Tulang Bawang Barat | 7.675 | bar: July W27 to August W35
35 | Lebong | Expansion | P1 PGM | 38.09 | 0.95225 | 1 | 0.011903 | 0.0095225 | 0.47612 | 0.3809 | 1 | 1 | mobility from Lubuk Linggau | Available 1 Dax KC2 |  |  | Already Have | have to contact Dax, then can start collection | Lebong | 0.47612 | bar: July W27
36 | Lingga | Expansion | P1 PGM | 63.31 | 1.5827 | 1 | 0.019784 | 0.015827 | 0.79137 | 0.6331 | 1 | 1 | mobility from Prabumulih | Available 1 Dax KC2 2 hours motorbike from Prabumulih | can start collection |  | Already Have |  | Lingga | 0.79137 | bar: July W27
37 | Lahat | Maintenance | P1 Atlas | 729.1 | 18.2275 | 1 | 0.22784 | 0.18227 | 9.1137 | 7.291 | 3 | 2 | mobility from Prabumulih | available 1 Dax KC2 |  | Suggest to Start | Already Have |  | Lahat | 9.1137
38 | Luwu Utara | Expansion | P1 PGM | 471.73 | 11.7933 | 1 | 0.14742 | 0.11793 | 5.8966 | 4.7173 | 2 | 2 | mobility from Kendari | Available 1 Dax KC360 11 hours motorbike from Kendari | risk, too far away | Suggest to Start | Already Have | have to contact Dax due to mobility program, then can start collection | Luwu Utara | 5.8966 | bar: July W27 to August W33
39 | Parigi Moutong | Expansion | P1 PGM | 575.66 | 14.3915 | 1 | 0.17989 | 0.14391 | 7.1957 | 5.7566 | 2 | 2 | mobility from Palu | available 1 Dax KC360 6,5 hours motorbike from Palu | risk, too far away |  | Already Have |  | Parigi Moutong | 7.1957 | bar: July W27 to September W37
40 | Palu | Maintenance | P1 Atlas | 1840.53 | 46.0132 | 1 | 0.57517 | 0.46013 | 23.0066 | 18.4053 | 6 | 5 | Palu | available 1 Dax KC2 |  | Suggest to Start | Already Have |  | Palu | 23.0066
41 | Minahasa Selatan | Expansion | P1 PGM | 798.77 | 19.9692 | 1 | 0.24962 | 0.19969 | 9.9846 | 7.9877 | 3 | 2 | mobility from Manado | Available 1 Dax KC2, 1 Dax KC360 2,5 hours motorbike from Manado | can start collection |  | Already Have |  | Minahasa Selatan | 9.9846 | bar: July W27 to August W32
42 | Minahasa Tenggara | Expansion | P1 PGM | 390.76 | 9.769 | 1 | 0.12211 | 0.09769 | 4.8845 | 3.9076 | 2 | 1 | mobility from Manado | Available 1 Dax KC2, 1 Dax KC360 2,5 hours motorbike from Manado | can start collection |  | Already Have |  | Minahasa Tenggara | 4.8845 | bar: August W34 to September W36
43 | Sumba Timur | Expansion | P0 PGM, P1 Atlas | 323.82 | 8.0955 | 1 | 0.10119 | 0.080955 | 4.0477 | 3.2382 | 2 | 1 | mobility from SBD |  |  | In Progress | Already Have |  | Sumba Timur | 4.0477 | bar: April W15 to May W19
44 | Surabaya | Maintenance | P1 Atlas | 5957.62 | 148.9405 | 3 | 1.8618 | 1.4894 | 24.8234 | 19.8587 | 7 | 5 | Surabaya | available 5 Dax KC2 |  |  | Already Have |  | Surabaya | 24.8234
45 | Bengkulu | Maintenance | P1 Atlas | 1600.95 | 40.0237 | 1 | 0.5003 | 0.40024 | 20.0119 | 16.0095 | 6 | 5 | Bengkulu | available 1 Dax KC2 |  | Suggest to Start | Already Have |  | Bengkulu | 20.0119
46 | Curup | Maintenance | P1 Atlas | 939.18 | 23.4795 | 1 | 0.29349 | 0.23479 | 11.7397 | 9.3918 | 3 | 3 | mobility from Lubuk Linggau | available 1 Dax KC2 |  | Suggest to Start | Already Have |  | Curup | 11.7397
47 | Sumbawa Besar | Maintenance | P1 Atlas | 374.29 | 9.3572 | 1 | 0.11697 | 0.093572 | 4.6786 | 3.7429 | 2 | 1 | mobility from Bima | available 1 Dax KC360 |  |  | Already Have |  | Sumbawa Besar | 4.6786
48 | Lamandau | Expansion | P1 PGM | 526.03 | 13.1507 | 1 | 0.16438 | 0.13151 | 6.5754 | 5.2603 | 2 | 2 | mobility from Pontianak | Available 1 Dax (Dax KC360) 10 hours motorbike from Pontianak | risk, too far away |  | Need KC2 | have to contact Dax due to mobility program, then can start collection | Lamandau | 6.5754 | bar: July W27 to August W34
49 | Pontianak | Maintenance | P1 Atlas | 1887.01 | 47.1752 | 1 | 0.58969 | 0.47175 | 23.5876 | 18.8701 | 6 | 5 | Pontianak | available 1 Dax KC360 |  |  | Need KC2 |  | Pontianak | 23.5876
50 | Ketapang | Expansion | P1 Atlas | 1023.59 | 25.5897 | 5 | 0.31987 | 0.2559 | 2.559 | 2.0472 | 1 | 1 | mobility from Pontianak | available 1 Dax KC360 |  |  | Need KC2 |  | Ketapang | 2.559
51 | Sintang | Expansion | P1 Atlas | 39.28 | 0.982 | 1 | 0.012275 | 0.00982 | 0.491 | 0.3928 | 1 | 1 | mobility from Pontianak | available 1 Dax KC360 |  |  | Need KC2 |  | Sintang | 0.491
52 | Manokwari | Expansion | P1 Atlas | 399.93 | 9.9983 | 1 | 0.12498 | 0.099983 | 4.9991 | 3.9993 | 2 | 1 | mobility from Sorong | available 1 Dax KC360 |  |  | Need KC2 |  | Manokwari | 4.9991
53 | Tarakan | Maintenance | P1 Atlas | 768.57 | 19.2142 | 1 | 0.24018 | 0.19214 | 9.6071 | 7.6857 | 3 | 2 | Tarakan | available 1 Dax KC360 |  |  | Need KC2 |  | Tarakan | 9.6071
| Cilegon | Expansion |  | 1054.88 | 26.372 | 1 | 0.32965 | 0.26372 | 13.186 | 10.5488 | 4 | 3 |  |  |  | Suggest to Start | bar: January W4 to February W6
| Pematang Siantar | Expansion |  | 1318.93 | 32.9732 | 1 | 0.41217 | 0.32973 | 16.4866 | 13.1893 | 5 | 4 |  |  |  | Suggest to Start | bar: January W4 to February W6
| Balige | Expansion |  | 305.88 | 7.647 | 1 | 0.095588 | 0.07647 | 3.8235 | 3.0588 | 1 | 1 |  |  |  | Suggest to Start | bar: January W4 to February W6
54 | Labuan Bajo | Maintenance | P0 PGM | 182.28 | 4.557 | 1 | 0.056962 | 0.04557 | 2.2785 | 1.8228 | 1 | 1 | Labuan Bajo | Available 1 Dax (Dax KC2) | risk, no current PE |  | No Dax Available |  | Labuan Bajo | 2.2785 | bar: January W4 to February W6
55 | Ternate | Maintenance | P0 Atlas | 308.69 | 7.7172 | 1 | 0.096466 | 0.077172 | 3.8586 | 3.0869 | 1 | 1 | Ternate | available 6 Dax (1 Dax Kartacam 360, 5 Dax BYOD) |  |  | No Dax Available |  | Ternate | 3.8586 | bar: January W4 to March W13

## Q3 Collection Plan
City | UKM Target | Basic Incentive | >95% Bonus Coverage | Insurance | Data Plan | Miscellaneous (5%) | Estimation Incentive (IDR) | Estimation Incentive (USD)

## 2H Plan Collection (hidden)
City | status collection | PIC | Check | Remarks
Bali | in progress | nuril | TRUE
Palangkaraya |  | nuril | TRUE
Cirebon |  | nuril | FALSE | Not planned this year
Jember |  | nuril | FALSE | Not planned this year
Bandung | completed | nuril | TRUE
Lampung |  | nuril | FALSE | Not planned this year
Dumai |  | nuril | FALSE | Not planned this year
Palu |  | nuril | TRUE
Pangkal Pinang |  | nuril | FALSE | Not planned this year
Banjarmasin |  | nuril | FALSE | Not planned this year
Serang |  | nuril | FALSE | Not planned this year
Surabaya |  | nuril | FALSE
Medan | completed | nuril | FALSE
Padang |  | nuril | FALSE | need to ship KC2
Pekalongan |  | nuril | FALSE | Not planned this year
Madiun |  | nuril | FALSE | Not planned this year
Tarakan |  | nuril | FALSE | need to ship KC2
Jakarta | completed | nuril | FALSE
Pekanbaru |  | nuril | FALSE | Not planned this year
Solo | completed | nuril | FALSE
Karawang |  | nuril | FALSE | P2 Atlas
Kediri |  | nuril | FALSE | Not planned this year
Palembang | completed | nuril | FALSE
Tasikmalaya |  | nuril | FALSE | Not planned this year
Kudus |  | santi | FALSE | Not planned this year
Mamuju |  | santi | FALSE | P2 Atlas
Cilegon |  | santi | FALSE | Not planned this year
Aceh |  | santi | FALSE | Not planned this year
Batam |  | santi | FALSE | Not planned this year
Pontianak |  | santi | FALSE | need to ship KC2
Kupang | completed | santi | FALSE
Bengkulu |  | santi | TRUE
Semarang | completed | santi | FALSE
Purwakarta |  | santi | FALSE | Not planned this year
Makassar |  | santi | FALSE | Not planned this year
Jayapura |  | santi | FALSE | Not planned this year
Banyumas |  | santi | FALSE | Not planned this year
Malang | in progress | santi | FALSE
Lahat |  | santi | TRUE
Kedu Raya |  | santi | FALSE | Not planned this year
Jambi |  | santi | FALSE | Not planned this year
Pematang Siantar |  | santi | FALSE | Not planned this year
Yogyakarta | completed | santi | FALSE
Sumba Timur |  | santi | FALSE
Samarinda |  | santi | FALSE | Not planned this year
Manado | completed | santi | FALSE
Lebak |  | santi | FALSE
Ternate |  | santi | FALSE | need to ship KC2
Balikpapan |  | fachri | TRUE
Ambon |  | fachri | TRUE | P2 Atlas
Gorontalo | In Progress | fachri | TRUE
Tanjung Pandan |  | fachri | TRUE | P2 Atlas
Pelabuhan Ratu |  | fachri | TRUE
Tabalong |  | fachri | TRUE
Mataram | completed | fachri | FALSE
Kebumen | completed | fachri | TRUE
Kendari |  | fachri | FALSE | Not planned this year
Garut |  | fachri | FALSE | P2 Atlas
Madura | In Progress | fachri | FALSE
Cianjur |  | fachri | FALSE | Not planned this year
Sukabumi |  | fachri | FALSE | P2 Atlas
Sumbawa Besar |  | fachri | FALSE
Kotamobagu |  | fachri | TRUE | P2 Atlas
Curup |  | fachri | TRUE
Labuan Bajo |  | fachri | FALSE
Bima | In Progress | fachri | TRUE
Pandeglang |  | fachri | TRUE
Cilacap | completed | fachri | TRUE
Balige |  | fachri | FALSE | Not planned this year
Tanjung Pinang | completed | fachri | TRUE
Baturaja |  | fachri | FALSE | Not planned this year
Sorong | In Progress | fachri | TRUE
Hulu Sungai Utara |  | fachri | TRUE

## City Plan (P2) (hidden)
[5 empty] | Kondisi Ideal |  |  |  | Estimasi Penyelesaian Project
No | Target City | Type | Priority | Target Navigable UKM | Target Productivity per Week | Dax Number | Dax Number (80 UKM/Week) | Dax Number (100 UKM/Week) | Week Estimation (80 UKM/Week) | Week Estimation (100 UKM/Week) | Month Estimation (80 UKM/Week) | Month Estimation (100 UKM/Week) | Driver Status | Driver Availability | Status | Status 2H | Remarks | Collection Timeline |  | January |  |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  |  | November |  |  |  | December |  |  |  |  | Week Counts
|  |  |  | Satuan: UKM | Satuan: UKM/Week | Satuan: DAX | Satuan: DAX | Satuan: DAX | Satuan: Week | Satuan: Week | Satuan: Month | Satuan: Month | [5 empty] | Target City | Week Estimation | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W1
1 | Karawang | Maintenance | P2 Atlas | 2289 | 57.225 | 6 | 0.71531 | 0.57225 | 4.7687 | 3.815 | 2 | 1 | Jabo | available 18 Dax KC2 |  |  |  | Karawang | 4.7687
2 | Sukabumi | Maintenance | P2 Atlas | 3717 | 92.925 | 6 | 1.1616 | 0.92925 | 7.7438 | 6.195 | 2 | 2 | Jabo | available 18 Dax KC2 |  |  |  | Sukabumi | 7.7438
3 | Garut | Maintenance | P2 Atlas | 3129 | 78.225 | 7 | 0.97781 | 0.78225 | 5.5875 | 4.47 | 2 | 2 | mobility from Bandung | available 7 Dax KC2 |  |  |  | Garut | 5.5875
4 | Mamuju | Maintenance | P2 Atlas | 1514 | 37.85 | 1 | 0.47313 | 0.3785 | 18.925 | 15.14 | 5 | 4 | Mamuju | available 1 Dax KC360 |  |  |  | Mamuju | 18.925
5 | Ambon | Maintenance | P2 Atlas | 505 | 12.625 | 1 | 0.15781 | 0.12625 | 6.3125 | 5.05 | 2 | 2 | Ambon | available 1 Dax KC360 |  |  |  | Ambon | 6.3125
6 | Tanjung Pandan | Maintenance | P2 Atlas | 3236 | 80.9 | 2 | 1.0112 | 0.809 | 20.225 | 16.18 | 6 | 5 | mobility from Pangkal Pinang | available 1 Dax KC2 |  |  |  | Tanjung Pandan | 20.225
7 | Sibolga | Expansion | P2 Atlas | 25 | 0.625 | 1 | 0.0078125 | 0.00625 | 0.3125 | 0.25 | 1 | 1 | mobility from Pekanbaru | Available 1 Dax (Dax KC2) |  |  |  | Sibolga | 0.3125
8 | Kotamobagu | Maintenance | P2 Atlas | 151 | 3.775 | 1 | 0.047188 | 0.03775 | 1.8875 | 1.51 | 1 | 1 | Kotamobagu | available 1 Dax KC360 |  |  |  | Kotamobagu | 1.8875
0

## Total Dax and Equipment (hidden)
P0, P1, and P2 CITIES |  |  |  | P0 CITIES
City | Dax | Total Dax | Equipment (KC2) | City | Dax | Total Dax | Equipment (KC2)
Bali | Bali | 5 | already have | Bali | Bali | 5 | already have
Bali (ToDo from 2024) |  |  |  | Bali (ToDo from 2024)
Bandung | #REF! | 6 | already have | Bandung | Bandung | 6 | already have
Banjar |  | 1 | need KC2 | Cilacap
Pangandaran |  |  |  | Bekasi | Jabo | 18 | already have
Cilacap |  |  |  | Bogor
Garut |  |  |  | Jakarta
Pelabuhan Ratu | Jabo | 18 | already have | Tangerang
Bekasi |  | 3 | need KC2 | Depok
Bogor |  |  |  | Nusantara (IKN) | Samarinda | 1 | already have
Jakarta |  |  |  | Pangkalan Bun | Medan | 2 | already have
Lebak |  |  |  | Kabanjahe
Pandeglang |  |  |  | Medan
Tangerang |  |  |  | Rantau Prapat | Balige | 1 | need KC2
Depok |  |  |  | Tanjung Pinang | Batam | 1 | already have
Karawang |  |  |  | Padang Sidempuan | Padang | 1 | need KC2
Sukabumi |  |  |  | Tana Toraja | Makassar | 2 | already have
Balikpapan | Samarinda | 1 | already have | Luwu
Nusantara (IKN) |  |  |  | Hulu Sungai Selatan | Banjarmasin | 1 | already have
Bangka | Pangkal Pinang | 1 | already have | Hulu Sungai Tengah
Tanjung Pandan |  | 1 | need KC2 | Kota Lubuk Linggau | Lubuk Linggau | 1 | already have
Barito Selatan | Palangkaraya | 1 | already have | Kupang | Kupang | 1 | already have
Barito Timur |  |  |  | Labuan Bajo | Labuan Bajo | 1 | already have
Katingan |  |  |  | Bandar Jaya | Lampung | 1 | already have
Pangkalan Bun | [5 empty] | 2 | need KC2
Batu Bara | Medan | 2 | already have | Prabumulih | Prabumulih | 1 | already have
Kabanjahe |  |  |  | Luwuk | Palu | 1 | already have
Kota Langsa |  |  |  | Madura | Surabaya | 5 | already have
Medan |  |  |  | Malang | Malang | 2 | already have
Tanjung Balai | Balige | 2 | need KC2 | Manado | Manado | 2 | already have
Rantau Prapat |  |  |  | Mataram | Mataram | 2 | already have
Bener Meriah | Aceh | 1 | already have | Sumba Barat
Kota Sabang |  |  |  | Sumba Barat Daya
Lhokseumawe |  |  |  | Sumba Timur
Bintan | Batam | 1 | already have | Merangin | Jambi | 1 | already have
Tanjung Pinang |  |  |  | Muara Bungo
Dharmasraya | Padang | 2 | need KC2 | Sarolangun
Kota Sawahlunto |  |  |  | Palembang | Palembang | 1 | already have
Kota Solok |  |  |  | Muara Enim |  | 1 | need KC2
Pasaman Barat |  |  |  | Solo | Yogyakarta | 5 | already have
Padang Sidempuan |  |  |  | Yogyakarta
Padang |  |  |  | Bima | Bima | 1 | need KC2
Enrekang | Makassar | 2 | already have | Semarang | Semarang | 3 | already have
Tana Toraja |  |  |  | Sorong | Sorong | 1 | need KC2
Luwu |  |  |  | Ternate | Ternate | 1 | need KC2
Hulu Sungai Selatan | Banjarmasin | 1 | already have
Hulu Sungai Tengah
Hulu Sungai Utara
Kotabaru
Tabalong
Indragiri Hilir | Pekanbaru | 1 | already have
Sibolga
Kota Lubuk Linggau | Lubuk Linggau | 1 | already have
Kupang | Kupang | 1 | already have
Labuan Bajo | Labuan Bajo | 1 | already have
Manggarai
Lamandau | Pontianak | 4 | need KC2
Pontianak
Ketapang
Sintang
Lampung Utara | Lampung | 1 | already have
Tanggamus |  | 2 | need KC2
Tulang Bawang
Tulang Bawang Barat
Bandar Jaya
Lebong | Curup | 1 | need KC2
Curup
Lingga | Prabumulih | 1 | already have
Prabumulih
Lahat
Luwu Utara | Mamuju | 1 | need KC2
Mamuju
Luwuk | Palu | 1 | already have
Parigi Moutong
Palu
Madura | Surabaya | 5 | already have
Surabaya
Malang | Malang | 2 | already have
Manado | Manado | 2 | already have
Minahasa Selatan
Minahasa Tenggara
Mataram | Mataram | 2 | already have
Merangin | Jambi | 1 | already have
Muara Bungo
Sarolangun
Palembang | Palembang | 1 | already have
Muara Enim |  | 1 | need KC2
Solo | Yogayakarta | 5 | already have
Yogyakarta
Kebumen
Sumba Barat | Bima | 1 | need KC2
Sumba Barat Daya
Sumba Timur
Bima
Sumbawa Besar
Semarang | Semarang | 3 | already have
Sorong | Sorong | 1 | need KC2
Manokwari
Gorontalo | Gorontalo | 1 | need KC2
Ternate | Ternate | 1 | need KC2
Bengkulu | Bengkulu | 1 | need KC2
Tarakan | Tarakan | 1 | need KC2
Ambon | Ambon | 1 | need KC2
Kotamobagu | Kotamobagu | 1 | need KC2
Nusantara (IKN) | mobility from Samarinda | 1 | already have

## Sheet6 (hidden)
Collection Timeline |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  |  | May |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
Target City | Week Estimation | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41 | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W1
Target City | Week Estimation
Bali | 16.0256 | bar: Feb W7; Mar W11 to May W19
Bandung | 23.1973 | bar: Feb W7; Mar W11 to Jun W26
Medan | 18.0198 | bar: Feb W7; Mar W11 to May W21
Bekasi | 13.9254 | bar: Feb W7; Mar W11 to Apr W17
Bogor | 9.6279 | bar: Feb W7; Mar W11 to Mar W13
Jakarta | 31.5586 | bar: Feb W7; Mar W11 to Aug W35
Tangerang | 41.3204 | bar: Feb W7; Mar W11 to Nov W45
Tana Toraja | 17.4324 | bar: Feb W7; Mar W11 to May W21
Hulu Sungai Selatan | 2.2006
Hulu Sungai Tengah | 3.2803 | bar: Mar W11
Kota Lubuk Linggau | 12.474 | bar: Feb W7; Mar W11 to Apr W16
Kupang | 9.7473 | bar: Feb W7; Mar W11 to Mar W13
Labuan Bajo | 2.6039
Luwuk | 1.4001
Malang | 27.5179 | bar: Feb W7; Mar W11 to Jul W31
Manado | 12.5274 | bar: Feb W7; Mar W11 to Apr W16
Mataram | 11.7206 | bar: Feb W7; Mar W11 to Apr W15
Merangin | 5.469 | bar: May W21 to Jun W26
Muaro Bungo | 7.1351 | bar: Feb W7; Mar W11
Sarolangun | 6.408 | bar: Mar W13 to May W19
Palembang | 28.2921 | bar: Feb W7; Mar W11 to Aug W32
Solo | 6.7947 | bar: Feb W7
Yogyakarta | 18.1646 | bar: Feb W7; Mar W11 to May W22
Sumba Barat | 2.8184
Sumba Barat Daya | 5.188 | bar: Mar W11 to Mar W13
Sumba Timur | 4.6253 | bar: Apr W15 to May W19